## Checklist
NOERR
Upgrade NOERR to latest VIZOR
[Date]
Task | Complete | Time (min) | Comments (optional) | Reference
Prepare VIT
Upgrade their DBs to 2.5.2 RTM if not already (may need to be done on a cloned server to not impact production) |  | 60 | This might already be the done for NOERR. Need to verify before we proceed with the upgrade.
Ensure the customer knows that they can no longer create/update queries, sorts, views, etc. |  | 5
Create backups of DBs |  | 30
Backup the CustomizedFiles folder |  | 5
Upgrade Vizor
Stop Mq.* services |  | 5
Run the script to delete the queries, etc |  | 5 | Upgrade to 304\scripts.sql
Verify that the remaining queries are using the correct ID for U304 |  | 15 | Assets$By$Assigned$to$Person' = ID should be 61 instead of 55
Run the batch file to rename customized files that wont be needed |  | 5 | Upgrade to 304\renamecustfiles.bat
Run the Vizor252Updates process to get them to U304. Do NOT generate views yet. |  | 60 | http://www.vector-networks.com/downloads/vizor/2.50.2/Updates/Vizor252Updates.zip
Manual Changes
Verify that script errors given during Vizor252Updates are not a problem |  | 60
Remove any duplicate web views added
Finalize Upgrade
Copy updated customized files to Vizor server |  | 5 | Upgrade to 304\CustomizedFiles
Apply workflows for all projects |  | 10
Generate views and admin |  | 30
Configure/schedule the AD import |  | 15
Start Mq.* services |  | 5
Testing
Vector testing |  | 60
Customer acceptance testing |  | 120